## Content_Mgt_Issues
| Environment | Tenants | Description | Issue
1 | UAT | All 3 | Creation of banner or pages and do Publish | Status changes to Approved and after several hours its changes to Published
2 | UAT | All 3 | 1. Create banner and Submited banner. | Edit Banner not getting details correctly:(asking to fill all mandate fields)
2. Edit--Assign Back then status changed to Rejected.
3. Again Edit-->Submit(asking to fill all mandate fields) where as in KT Session it dint ask
3 | UAT | All 3 | Images KT is not provided | Has an existing issue
4 | UAT | All 3 | Notifications | Confirm with Saran
5 | UAT | All3 | Speridian_ContentManagement_AccountAdminLanding_Pages_Flow | Not tested verification of page changes by logging in Support user
below:
1. Document changes
2. Image changes (Image upload is not working)
as status is not getting changed immediately. But code is added.
3. Unpublish also done but cannot test.
4. Preview is taking too long but code is added.
6 | UAT | All3 | Speridian_ContentManagement_EmployeeLanding_Pages_Flow | Not tested verification of page changes by logging in Support user
below:
1. Document changes
2. Image changes (Image upload is not working)
as status is not getting changed immediately. But code is added.
3. Unpublish also done but cannot test.
4. Preview is taking too long but code is added.
7 | UAT | FBMC, Speridian | FBMC_ContentManagement_Documents_AddwordDoc_Flow | we are not able to publish document
8 | UAT | IHA, FBMC, Speridian | FBMC_ContentManagement_Documents_AddPdf_Excel_Doc_Flow | we are not able to publish document and not able to verify through support user login
Sometimes when copy the Document, its created with previous day date, which is wrong.
9 | UAT | IHA, FBMC, Speridian | Speridian_ContentManagement_Images_Flow | Existing Issue, image dont show when upload.
10 | UAT | IHA | IHA_ContentManagement_TerminateAccountwithAgencyContact_Notifications_Flow | Taking more time to trigger Email logs

## FBMC_BusinessRules_Issues
TC ID | Issue
FBMC_TerminatePolicy_Lake Sumter_BasicAD&D_turns70 | Termination dt is calculating wrong
FBMC_TerminatePolicy_JacksonHealthSystem_Turns65 | Termination dt is calculating wrong
FBMC_Florida_ChangeRate_turns_70or75 | Termination dt is calculating wrong
FBMC_Flagler_ChangeBenifitamt_turns_70or75 | Termination dt is calculating wrong
FBMC_Daytona_Coverageamt_ChangeLifeBenefitReduction_turns_70or75 | Termination dt is calculating wrong

## IHA_BrokerMgt_Issues
Blocker | Comments | Status
After Editing the Agency name unable to Save it. | When we are trying to edit the agency name and click on Save Button, the Save button is not working. | Not Resolved
The scripting part is completed only execution part is left.

## Billing&Payments_Issues
| Environment | Tenants | Issue | Screenshot
1 | UAT | FBMC | The user is not able to see the overpaid amount inside the refund center.

## IHA_User_Admin_Registration_Iss
3 TCs are implemented but not tested as its not working. Broker Management Marketing Web Member Call Center The above roles are not working and same confirmed from Saran.

## Transactions_IHA_Issue
Blocked as the Multi Transaction Type related reports are failing while download. Redmine# :- 49098

## RC_Employee
1 | Renewal Center(Not able to see Tile for Employee)