## Tenant Level
S.No | Type | Functionality/Module/Flow | Sub Level 1 | Sub Level 2 | Status | Issue/Comment
1 | Tenant Level | Create new tenant through TOB
2 |  | Registration on new tenant using the regsitration process in TOB
3 |  | Upload tenant logo
4 |  | Tenant Level Modules
5 |  | Content Management | Pages
6 |  |  | Review
7 |  |  | Documents
8 |  |  | Baner
9 |  |  | Images
10 |  |  | Notifications
11 |  |  | Section titles
12 |  | Billing & Payment | Cash Ledger
13 |  |  | Reconcillation Summary
14 |  |  | Account Receivable | Import
15 |  |  |  | Delete
16 |  |  |  | Post to ledger
17 |  |  | Delinquecy List
18 |  |  | Delinquency (FRS & CPRB)
19 |  |  | Schedule Payment | Add
20 |  |  |  | Generate
21 |  |  |  | Capture
22 |  |  | Account Payable | Generate Payable
23 |  |  |  | Review and Finalize
24 |  |  |  | Generate Voucher
25 |  |  |  | Generate Remittance Files
26 |  |  |  | Export
27 |  |  |  | Void Payables
28 |  |  |  | Cancel Refund
29 |  |  |  | Merge Refund
30 |  |  | Refund Center | Import
31 |  |  |  | Add refund
32 |  |  |  | Approve All
33 |  |  |  | Hold All
34 |  |  |  | Export
35 |  |  | Pension Authority File Generation
36 |  |  | Vendor ACH File Generation
37 |  | Communication | Correspondence
38 |  |  | Email Log
39 |  | Reports
40 |  | User Administration | User Profile
41 |  |  | Group Contact user
42 |  |  | Login History
43 |  | Support User
44 |  | Comments Roaster
45 |  | Internal | BA Support Activities
46 |  |  | Upload Logo
47 |  | Tenant Level Settings | Global Settings
48 |  |  | Business Segments
49 |  |  | Account Specific
50 |  | Global Member Search | Employee Search
51 |  |  | Advance Search
52 |  | Tenant Notification
53 |  | Tenant Profile | Profile
54 |  |  | Change Password
55 |  |  | Logout

## Group Level
S.No | Product Level | Functionality/Module/Flow | Sub Level 1 | Sub Level 2 | Sub Level 3 | Status | Issues/Comment
1 | Group Level | New Group Load - FBMC |  |  |  |  | 50
2 |  | New Group Load - IHA
3 |  | New Product and rate setup in DB |  |  |  |  | 50
4 |  | Group Load with Plan association |  |  |  |  | 50
5 |  | Administration | Employee Administration | Member Search
6 |  |  |  | Advance Search
7 |  |  |  | Add Employee
8 |  |  |  | Load Roaster | Add Employee
9 |  |  |  |  | Terminate Employee
10 |  |  |  |  | Payment Profile
11 |  |  |  | Activate Eligibility
12 |  |  |  | Request Online Access
13 |  |  |  | Export
14 |  |  | Group Administration | Group Details
15 |  |  |  | Contacts | Add Contact
16 |  |  |  | Broker
17 |  |  |  | Attachements
18 |  |  |  | Note
19 |  |  | Benefit Information | Billing Location
20 |  |  |  | Classes
21 |  |  |  | Benefit Plans
22 |  |  |  | Divisions
23 |  | Manage Coverage | View Coverage | Member Search
24 |  |  |  | Advance Search
25 |  |  |  | Enrollment Notification
26 |  |  |  | Enrollment Roaster
27 |  |  |  | Export
28 |  |  | Renewal | Member Search
29 |  |  |  | Advance Search
30 |  |  |  | Enrollment Notification
31 |  |  |  | Enrollment Roaster
32 |  |  |  | Export
33 |  | Reports | View Report
34 |  |  | Create Reports
35 |  | Comments Roaster
36 |  | Group level setting | Group Contribution Setup
37 |  |  | Group Preference Setup | Administration
38 |  |  |  | Employee Access
39 |  |  |  | Effective & Termination rule setup
40 |  |  |  | Employee Enrollment
41 |  |  |  | Group
42 |  |  |  | Billing
43 |  |  |  | Product
44 |  |  | Class Preference
45 |  |  | Passive renewal Setup
46 |  | Group Logo upload
47 |  | FAQ
48 |  | Contact Us
49 |  | Notification
50 |  | Loading Plan attribules
51 |  | Loading SBC documents
52 |  | Upload carrier Logo
53 |  | Landing page creation for the group
54 |  | Create BA/CA user
55 |  | Regsistration of BA and CA
56 |  | Login with BA and CA
57 |  | Employee creation from TPA
58 |  | Employee creation from BA
59 |  | Employee creation and enrollment

## FBMC
Fringe Benefits Management Company |  |  |  |  | Total Flows | Completed | %
Scenario/Flow | Test Status | QA Comments | Assignee | count | 187 | 62 | 33.1551
TPA LOGIN
Login | Completed |  |  | 6
Tenant Dashboard | Completed |  |  | 40
Group Dashboard | Completed |  |  | 30
Add Employee | Completed |  |  | 60
Activate employee | Completed |  |  | 3
Submit employee | Completed |  |  | 3
Activate and Enroll Employee | Completed |  |  | 30
Decline all coverage | Completed |  |  | 3
Terminate Medical | Completed |  |  | 2
Terminate Medicare | Completed |  |  | 3
Terminate Ancillary | Completed |  |  | 3
Summary Verification | Completed |  |  | 3
View benefits and SBC | Completed |  |  | 5
CC Letter verification | Completed |  |  | 2
Renroll Medical | Completed |  |  | 50
Renroll Medicare | Completed |  |  | 5
Reenroll Ancillary | Completed |  |  | 5
Change Plan Medical | Completed |  |  | 5
Change Plan Medicare | Completed |  |  | 5
Change Plan Ancillary | Completed |  |  | 5
Change coverage amount | In Progress |  |  | 5
Enroll and maintenance with Rate edit plan | In Progress |  |  | 5
QE on Medical | Completed |  |  | 5
QE Medicare | Completed |  |  | 5
QE Ancillary | Completed |  |  | 5
Update covered Members - Medical | Completed |  |  | 5
Update covered Members - Ancillary | Completed |  |  | 5
Terminate Employee | Completed |  |  | 5
Employe Rehire &Enroll | Completed |  |  | 5
Reinstate employee | Completed |  |  | 15
Load &Enrollment Roster | Completed |  |  | 20
Terminate Roster | Completed |  |  | 30
Payment Profile Roster | Completed |  |  | 25
Reports (Create, View and Export) | Completed |  |  | 20
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | In Progress |  |  | 60
Policy Setup |  |  |  | 40
Policy Info |  |  |  | 60
Group preferance(effective date, termination date) |  |  |  | 50
Retro enrollment with retro period | Completed |  |  | 10
Retro termination with retro period | Completed |  |  | 20
Request online access |  |  |  | 10
Send Enrollment Notification |  |  |  | 10
Reset Password |  |  |  | 10
Lock and rate | NA |  |  | 5
Employee Administration
Employee Administration Dashboard and sub modules | Completed |  |  | 50
Mangae coverage
Manage coverage Dashboard and sub modules | Completed |  |  | 50
Renewal center Dashboard
Renewal center Dashboard and sub modules | Completed |  |  | 50
Renewal load and passive renewal | NA |  |  | 150
Group Load
New group load | NA |  |  | 50
Product and rate load | NA |  |  | 50
Plan association | NA |  |  | 50
Billing and Payment
Statement
Statement Generation | NA |  |  | 10
Account Summary |  |  |  | 100
Vendor account |  |  |  | 100
Real Time - Adjustment generation |  |  |  | 250
Payment Profile creation |  |  |  | 40
Statement PDF Generation
Invoice PDF validation report | NA |  |  | 5
PDF generation | NA |  |  | 10
Moving it to Printer | N/A |  |  | 5
Less payment through roster/Online |  |  |  | 20
Verify the payment is not applied for any line item |  |  |  | 10
Full payment through Roster/Online
Verify the payment is applied for all the line item. |  |  |  | 20
Overpaid through Roster/Online
Verify the payment is applied for all the line item |  |  |  | 20
Verify the overpaid negative amount available in outstanding balance |  |  |  | 20
Payment and Apply - Roaster/Online
NSF |  |  |  | 20
Void |  |  |  | 20
Stop |  |  |  | 20
Refund |  |  |  | 20
Refund Center
Verify the overpaid amount is displaying in the refund center. |  | KT Completed |  | 10
Approve/Hold the Refund |  | KT Completed |  | 10
Add manual refund |  | KT Completed |  | 20
Refund roaster | NA |  |  | 10
Partial refund |  | KT Completed |  | 10
Change Payee for refund |  | KT Completed |  | 15
Bulk refund approve | NA |  |  | 20
Refund in Account Payable
Verify the approved refund is reflecting in Account payable screen |  |  |  | 5
Review and Finalize the refund |  |  |  | 5
Generate the voucher for the refund record. |  |  |  | 5
Verify the refunded amount is displaying under customer active statement after refund process. |  |  |  | 20
Cash Ledger
Reconcilation summary |  | KT Completed |  | 10
Cash Ledger screen |  | KT Completed |  | 20
Account Receivable
Payment Import | NA |  |  | 30
Pyment posting | NA |  |  | 5
Apply Process | NA |  |  | 25
Bulk Payment Import | NA |  |  | 10
Post receivables download | NA |  | N/A
Account Payable
Generate payables | NA |  |  | 20
Finalize payable | Only for refund | KT Completed |  | 10
Void Payable | NA |  |  | 10
Cancel Refund |  | KT Completed |  | 5
Merge and Finalize | NA |  |  | 20
Remittance File Generation | NA |  |  | 20
Scheduled Payment
10th ACH schedule | NA |  |  | 15
22nd ACH Schedule | NA |  |  | 15
Add Scheduled Payment | NA |  |  | 10
Generate Scheduled Payment | NA |  |  | 10
Capture Scheduled Payment | NA |  |  | 10
Delinquency FRS & CPRB
Delinquency roaster | NA |  |  | 5
Generate Delinquency letter | NA |  |  | 10
With FRS | NA |  |  | 10
Without FRS | NA |  |  | 10
Pension Authority File Generation
FRS-408 generation |  | KT Completed |  | 10
FRS-409 Generation |  | KT Completed |  | 10
CPRB Legal |  | KT Completed |  | 10
CPRB Non Legal |  | KT Completed |  | 10
PHT Annually |  | KT Completed |  | 10
Vendor ACH file generation
ACH file generation |  | KT Completed |  | 10
Remittance Automation
Remittance report generation(100+ reports) | NA |  |  | 100
User Administration
User Profile
Add Profile |  | KT Completed |  | 15
Register Profile |  | KT Completed |  | 15
Edit Profile |  | KT Completed |  | 15
Delete Profile |  | KT Completed |  | 5
Group Contact User |  | KT Completed
Add Profile |  | KT Completed |  | 15
Register Profile |  | KT Completed |  | 15
Edit Profile |  | KT Completed |  | 15
Delete Profile |  | KT Completed |  | 10
Login History |  | KT Completed
Verify login history |  | KT Completed |  | 5
Support User |  | KT Completed
Support User Login |  | KT Completed |  | 20
Comment Roaster
Comment Roster Upload | NA |  |  | 10
Audit Report Generation
Daily Reports | NA |  |  | 6
EEF-2001 report | NA |  |  | 2
Remittance discrepency reports | NA |  |  | 6
Correspondence Center
New Enrollment Letter |  | KT Completed |  | 10
Change Coverage letter |  | KT Completed |  | 10
Manual Termination Letter |  | KT Completed |  | 10
Statement |  | KT Completed |  | 10
ACH and Check rejection letter |  | KT Completed |  | 10
ACH Authorization form |  | KT Completed |  | 10
FRS Authorization form |  | KT Completed |  | 10
Delinquency letter |  | KT Completed |  | 10
FRS Kick out letter |  | KT Completed |  | 10
Business Automation Rule
Automation Rule |  | KT Completed |  | 50
BA LOGIN
BA Login
Add Employee | Completed | KT Completed |  | 60
Add and Edit Beneficiary | Completed | KT Completed |  | 30
Activate and Enroll Employee | Completed | KT Completed |  | 30
Decline all coverage | Completed | KT Completed |  | 2
Terminate Medical | Completed | KT Completed |  | 3
Terminate Ancillary | Completed | KT Completed |  | 3
Summary Verification | Completed | KT Completed |  | 5
Reenroll Medical | Completed | KT Completed |  | 5
Reenroll Ancillary | Completed | KT Completed |  | 5
Change Plan Medical | Completed | KT Completed |  | 5
Change Plan Ancillary | Completed | KT Completed |  | 5
QE on Medical | Completed | KT Completed |  | 5
QE Ancillary | Completed | KT Completed |  | 5
Update covered Members - Medical | Completed | KT Completed |  | 5
Update covered Members - Ancillary | Completed | KT Completed |  | 5
BA review-Submit ad Submit all | N/A | KT Completed |  | 10
BA review-Reject and Reject all | N/A | KT Completed |  | 10
Terminate Employee | N/A | KT Completed |  | 5
Employee Rehire &Enroll | N/A | KT Completed |  | 15
Cobra enrollment | N/A | KT Completed
Load &Enrollment Roster | N/A | KT Completed |  | 20
Payment Profile Roster | N/A | KT Completed |  | 25
Terminate Roster | N/A | KT Completed |  | 30
Bulk Enrollment | N/A | KT Completed |  | 20
Reports | N/A | KT Completed |  | 20
Cascade Scenario | In Progress | KT Completed |  | 60
Policy Setup |  | KT Completed |  | 40
EMPLOYEE LOGIN
Employee Login |  | KT Completed
Employee Registration and Enrollment notification |  | KT Completed |  | 20
Add and Edit Beneficiary |  | KT Completed |  | 30
Enroll employee | Completed | KT Completed |  | 10
Decline all coverage | Completed | KT Completed |  | 2
Terminate Medical | Completed | KT Completed |  | 3
Terminate Ancillary | Completed | KT Completed |  | 3
Summary Verification | Completed | KT Completed |  | 5
Application Document | N/A | KT Completed
Reenroll Medical | N/A | KT Completed |  | 5
Reenroll Ancillary | Completed | KT Completed |  | 5
Change Plan Medical | Completed | KT Completed |  | 5
Change Plan Ancillary | Completed | KT Completed |  | 5
QE on Medical | Completed | KT Completed |  | 5
QE Ancillary | Completed | KT Completed |  | 5
Update covered Members - Medical | Completed | KT Completed |  | 5
Update covered Members - Ancillary | Completed | KT Completed |  | 5
Employee Rehire &Enroll | N/A | KT Completed |  | 15
Cascade Scenario | In Progress | KT Completed |  | 10
EDI FIle process
EDI FIle process |  |  |  | 100
Total |  |  |  | 3420
Scenario | Status
All Page Navigations
Scheduled Report Download
Adhoc report Download
CC letter download
View Summary Download
Upload and download the attachments
View SBC and benfit summary download | N/A
EDI Connection verification | N/A
Email trigger

## IHA
Independent Health Association |  |  |  | Total | Completed | % | Redmine
Scenario/Flow | Test Status | QA Comments | Assignee | 166 | 67 | 40.3614 | #22094
Super Admin LOGIN | [6 empty] | #22099
Login | Completed | [5 empty] | #22115
Tenant Dashboard | Completed | [5 empty] | #22119
Group Dashboard | Completed | [5 empty] | #22032
Add Employee | Completed | [5 empty] | #21894
Activate employee | Completed | [5 empty] | #21891
Submit employee | Completed | [5 empty] | #21152
Activate and Enroll Employee | Completed | [5 empty] | #23334
Decline all coverage | Completed | [5 empty] | #23351
Terminate Medical | Completed | [5 empty] | #23365
Terminate Medicare | Completed | [5 empty] | #23367
Terminate Ancillary | Completed | [5 empty] | #23456
Summary Verification | Completed | [5 empty] | #23457
View benefits and SBC | Completed
CC Letter verification | Completed
Renroll Medical | Completed
Renroll Medicare | Completed
Reenroll Ancillary | Completed
Change Plan Medical | Completed
Change Plan Medicare | Completed
Change Plan Ancillary | Completed
Change coverage amount | Completed
Enroll and maintenance with Rate edit plan | NA
QE on Medical | Completed
QE Medicare | Completed
QE Ancillary | Completed
Update covered Members - Medical | Completed
Update covered Members - Ancillary | Completed
Terminate Employee | Completed
Load &Enrollment Roster
Employe Rehire &Enroll | Completed
Reinstate employee | Completed
Terminate Roster
Payment Profile Roster
Reports (Create, View and Export)
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | In Progress
Policy Setup
Policy Info
Group preferance(effective date, termination date)
Retro enrollment with retro period | Completed
Retro termination with retro period | Completed
Request online access
Send Enrollment Notification
Reset Password
Cobra enrollment | Completed
User Administration
User Profile
Add User
User Registration
Edit User
Delete User
Group Contact User
Add BA/CA
User Registration
Edit User
Delete User
Login History
Login history tracking verification
Support User
Login through Support user
Login for all the types of accounts
Perform transactions through support user logins
Content Management
Landing Page (Tenant level)
Verify the landing page screen( Pages, Review, Documents,Banner,Images, Section tiles)
Add Pages
Review
Publish landing page for all type of logins
Unpublish landing page
Make Copy of landing page
Delete landing page
Document
Add document
Link document to section title
Publish document
Unpublish Document
Make copy of document
Delete document
Banners
Add Banner
Publish banner
Unpublish banner
Make a copy od banner
Delete banner
Images
Add Images
Use Image in landing pages
Delete images
Notification
Add Notification
Enable the notification
Edit Notification
Send notification through transaction
Disable Notification
Section Title
Add Section titles
Assign documents
Edit section titles
Delete Section titles
Broker Management
Add agency
Send notification
Terminate
Add contact
Add account
Transaction
Account transactions
Member transactions
BA LOGIN
BA Login
Add Employee | Completed
Add and Edit Beneficiary
Activate and Enroll Employee | Completed
Decline all coverage | Completed
Terminate Medical | Completed
Terminate Ancillary | Completed
Summary Verification | Completed
Reenroll Medical | Completed
Reenroll Ancillary | Completed
Change Plan Medical | Completed
Change Plan Ancillary | Completed
QE on Medical | Completed
QE Ancillary | Completed
Update covered Members - Medical | Completed
Update covered Members - Ancillary | Completed
BA review-Submit ad Submit all | Completed
BA review-Reject and Reject all | Completed
Terminate Employee | Completed
Employee Rehire &Enroll | Completed
Cobra enrollment | Completed
Load &Enrollment Roster
Payment Profile Roster
Terminate Roster
Bulk Enrollment
Reports
Cascade Scenario | In Progress
Policy Setup
EMPLOYEE LOGIN
Employee Login
Employee Registration and Enrollment notification
Add and Edit Beneficiary | Completed
Enroll employee | Completed
Decline all coverage | Completed
Terminate Medical | Completed
Terminate Ancillary | Completed
Summary Verification | Completed
Application Document | Completed
Reenroll Medical | Completed
Reenroll Ancillary | Completed
Change Plan Medical | Completed
Change Plan Ancillary | Completed
QE on Medical | Completed
QE Ancillary | Completed
Update covered Members - Medical | Completed
Update covered Members - Ancillary | Completed
Employee Rehire &Enroll | In Progress
Employee reinstate | In Progress
360 | In Progress

## Speridian
Speridian |  |  |  |  | Total | Completed | %
Scenario/Flow | Test Status | QA Comments | Assignee |  | 133 | 68 | 51.1278
TPA LOGIN
Login | Completed |  |  | 2023-01-17
Tenant Dashboard | Completed |  |  | 2023-01-17
Group Dashboard | Completed |  |  | 2023-01-17
Add Employee | Completed |  |  | 2023-01-17
Activate employee | Completed |  |  | 2023-01-17
Submit employee | Completed |  |  | 2023-01-17
Activate and Enroll Employee | Completed |  |  | 2023-01-17
Decline all coverage | Completed |  |  | 2023-01-17
Terminate Medical | Completed |  |  | 2023-01-17
Terminate Medicare | Completed |  |  | 2023-01-17
Terminate Ancillary | Completed |  |  | 2023-01-17
Summary Verification | Completed |  |  | 2023-01-17
View benefits and SBC | Completed |  |  | 2023-01-17
CC Letter verification | Completed |  |  | 2023-01-17
Renroll Medical | Completed |  |  | 2023-01-18
Renroll Medicare | Completed |  |  | 2023-01-18
Reenroll Ancillary | Completed |  |  | 2023-01-18
Change Plan Medical | Completed |  |  | 2023-01-18
Change Plan Medicare | Completed |  |  | 2023-01-18
Change Plan Ancillary | Completed |  |  | 2023-01-18
Change coverage amount | Completed |  |  | 2023-01-18
Enroll and maintenance with Rate edit plan | Completed |  |  | 2023-01-18
QE on Medical | Completed |  |  | 2023-01-18
QE Medicare | Completed |  |  | 2023-01-18
QE Ancillary | Completed |  |  | 2023-01-18
Update covered Members - Medical | Completed |  |  | 2023-01-18
Update covered Members - Ancillary | Completed |  |  | 2023-01-18
Terminate Employee | Completed |  |  | 2023-01-18
Employe Rehire &Enroll | Completed |  |  | 2023-01-19
Reinstate employee | Completed |  |  | 2023-01-19
Load &Enrollment Roster |  |  |  | 2023-01-19
Terminate Roster |  |  |  | 2023-01-19
Payment Profile Roster |  |  |  | 2023-01-19
Reports (Create, View and Export) |  |  |  | 2023-01-19
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | In Progress |  |  | 2023-01-19
Policy Setup |  |  |  | 2023-01-19
Policy Info |  |  |  | 2023-01-19
Group preferance(effective date, termination date) | Completed |  |  | 2023-01-19
Retro enrollment with retro period | Completed |  |  | 2023-01-19
Retro termination with retro period | Completed |  |  | 2023-01-19
Request online access |  |  |  | 2023-01-19
Send Enrollment Notification |  |  |  | 2023-01-19
Reset Password |  |  |  | 2023-01-19
User Administration
User Profile
Add User |  |  |  | 2023-01-20
User Registration |  |  |  | 2023-01-20
Edit User |  |  |  | 2023-01-20
Delete User |  |  |  | 2023-01-20
Group Contact User
Add BA/CA |  |  |  | 2023-01-20
User Registration |  |  |  | 2023-01-20
Edit User |  |  |  | 2023-01-20
Delete User |  |  |  | 2023-01-20
Login History
Login history tracking verification |  |  |  | 2023-01-20
Support User
Login through Support user |  |  |  | 2023-01-20
Login for all the types of accounts |  |  |  | 2023-01-20
Perform transactions through support user logins |  |  |  | 2023-01-20
Content Management
Landing Page (Tenant level)
Verify the landing page screen( Pages, Review, Documents,Banner,Images, Section tiles) |  |  |  | 2023-01-23
Add Pages |  |  |  | 2023-01-23
Review |  |  |  | 2023-01-23
Publish landing page for all type of logins |  |  |  | 2023-01-23
Unpublish landing page |  |  |  | 2023-01-23
Make Copy of landing page |  |  |  | 2023-01-23
Delete landing page |  |  |  | 2023-01-23
Document
Add document |  |  |  | 2023-01-23
Link document to section title |  |  |  | 2023-01-23
Publish document |  |  |  | 2023-01-23
Unpublish Document |  |  |  | 2023-01-23
Make copy of document |  |  |  | 2023-01-23
Delete document |  |  |  | 2023-01-23
Banners
Add Banner |  |  |  | 2023-01-23
Publish banner |  |  |  | 2023-01-23
Unpublish banner |  |  |  | 2023-01-23
Make a copy od banner |  |  |  | 2023-01-23
Delete banner |  |  |  | 2023-01-24
Images
Add Images |  |  |  | 2023-01-24
Use Image in landing pages |  |  |  | 2023-01-24
Delete images |  |  |  | 2023-01-24
Notification
Add Notification |  |  |  | 2023-01-24
Enable the notification |  |  |  | 2023-01-24
Edit Notification |  |  |  | 2023-01-24
Send notification through transaction |  |  |  | 2023-01-24
Disable Notification |  |  |  | 2023-01-24
Section Title
Add Section titles |  |  |  | 2023-01-24
Assign documents |  |  |  | 2023-01-24
Edit section titles |  |  |  | 2023-01-24
Delete Section titles |  |  |  | 2023-01-24
Email Log
Review email log |  |  |  | 2023-01-25
Resend Email |  |  |  | 2023-01-25
BA LOGIN
BA Login |  |  |  | 2023-01-25
Add Employee | Completed |  |  | 2023-01-25
Add and Edit Beneficiary |  |  |  | 2023-01-25
Activate and Enroll Employee | Completed |  |  | 2023-01-25
Decline all coverage | Completed |  |  | 2023-01-27
Terminate Medical | Completed |  |  | 2023-01-27
Terminate Ancillary | Completed |  |  | 2023-01-27
Summary Verification | Completed |  |  | 2023-01-27
Reenroll Medical | Completed |  |  | 2023-01-27
Reenroll Ancillary | Completed |  |  | 2023-01-27
Change Plan Medical | Completed |  |  | 2023-01-27
Change Plan Ancillary | Completed |  |  | 2023-01-27
QE on Medical | Completed |  |  | 2023-01-27
QE Ancillary | Completed |  |  | 2023-01-27
Update covered Members - Medical | Completed |  |  | 2023-01-27
Update covered Members - Ancillary | Completed |  |  | 2023-01-27
BA review-Submit ad Submit all | Completed |  |  | 2023-01-27
BA review-Reject and Reject all | Completed |  |  | 2023-01-27
Terminate Employee | Completed |  |  | 2023-01-30
Employee Rehire &Enroll | Completed |  |  | 2023-01-30
Cobra enrollment | N/A |  |  | 2023-01-30
Load &Enrollment Roster |  |  |  | 2023-01-30
Payment Profile Roster |  |  |  | 2023-01-30
Terminate Roster |  |  |  | 2023-01-30
Bulk Enrollment |  |  |  | 2023-01-30
Reports |  |  |  | 2023-01-30
Cascade Scenario | Completed |  |  | 2023-01-30
Policy Setup |  |  |  | 2023-01-30
EMPLOYEE LOGIN
Employee Login
Employee Registration and Enrollment notification |  |  |  | 2023-01-31
Add and Edit Beneficiary |  |  |  | 2023-01-31
Enroll employee | Completed |  |  | 2023-01-31
Decline all coverage | Completed |  |  | 2023-01-31
Terminate Medical | Completed |  |  | 2023-01-31
Terminate Ancillary | Completed |  |  | 2023-01-31
Summary Verification | Completed |  |  | 2023-01-31
Application Document | Completed |  |  | 2023-01-31
Reenroll Medical | Completed |  |  | 2023-01-31
Reenroll Ancillary | Completed |  |  | 2023-01-31
Change Plan Medical | Completed |  |  | 2023-01-31
Change Plan Ancillary | Completed |  |  | 2023-02-01
QE on Medical | Completed |  |  | 2023-02-01
QE Ancillary | Completed |  |  | 2023-02-01
Update covered Members - Medical | Completed |  |  | 2023-02-01
Update covered Members - Ancillary | Completed |  |  | 2023-02-01
Employee Rehire &Enroll | Completed |  |  | 2023-02-01
Cascade Scenario | In Progress |  |  | 2023-02-01

## Flow Count
Client | Test Case count |  | Product | Client | Test Flow Count | Completed | Progress %
FBMC | 3420 |  | EE | FBMC | 187 | 62 | 33.1551
IHA | 3471 |  |  | IHA | 166 | 67 | 40.3614
Speridian | 2940 |  |  | Speridian | 132 | 68 | 51.5152
Total | 9831 |  | Total |  | 485 | 197 | 40.6186
|  |  | Automate | 90% | 436.5 |  | 45.1835
Regression Suite - FBMC
Flow/Module | Test case count | Application type
Application access(Tenant level and Group level) | 76 | Web
New Enrollee | 150 | Web | HPE | Optima | 86
Maintenance Flow | 233 | Web |  | Avmed | 16
Roaster Functionality | 75 | Web & Excel
Adhoc reports | 20 | Web & Excel
Group/Tenant level settings | 180 | Web
Employee Administration | 60 | Web & Email
Manage Coverage | 50 | Web & Email
Renewal Center | 50 | Web & Email
Billing and Payment | 1260 | Web, Excel, PDF, scheduler and SFTP
User Administration | 140 | Web & Email
Support User | 20 | Web
Correspondence Center | 90 | Web and PDF
Business Automation rule | 50 | Web
BA Login | 428 | Web, Email and Excel
Employee Login | 138 | Web, Email and Excel
Group load | 150 | Back end process through DB
Renewal load | 100 | Back end process through DB
Passive renewal | 50 | Web & Back end process
EDI file process | 100 | EDI
Total | 3420
Regression Suite - IHA
Flow/Module | Test case count | Application type
Application access(Tenant level and Group level) | 100 | Web
New Enrollee | 150 | Web
Maintenance Flow | 250 | Web
Adhoc reports | 20 | Web & Excel
Group/Tenant level settings | 30 | Web
Employee Administration | 20 | Web & Email
Manage Coverage | 20 | Web & Email
Renewal Center | 20 | Web & Email
Carrier Response update | 150 | Web
Reporting | 100 | Web and Excel
Content Management | 945 | Web, Excel, PDF and Email
User Administration | 175 | Web & Email
Support User | 15 | Web
Communication | 25 | Web and Email
Broker Management | 100 | Web
Transactions | 20 | Web, XML and EDI
BA Login | 428 | Web, Email and Excel
Employee Login | 138 | Web, Email and Excel
Passive renewal | 200 | Web & EDI
Group load, Member load and other EDI activities | 565 | EDI and Web
Total | 3471
Regression Suite - Speridian
Flow/Module | Test case count | Application type
Application access(Tenant level and Group level) | 76 | Web
New Enrollee | 150 | Web
Maintenance Flow | 233 | Web
Adhoc reports | 20 | Web & Excel
Group/Tenant level settings | 180 | Web
Employer Contribution | 50 | Web
Employee Administration | 60 | Web & Email
Manage Coverage | 50 | Web & Email
Renewal Center | 50 | Web & Email
User Administration | 140 | Web & Email
Support User | 20 | Web
Content Management | 945 | Web, Excel, PDF and Email
BA Login | 428 | Web, Email and Excel
Employee Login | 138 | Web, Email and Excel
Group load | 150 | Back end process through DB
Renewal load | 100 | Back end process through DB
Passive renewal | 50 | Web & Back end process
EDI file process | 100 | EDI
Total | 2940

## IHA Modules
Module | Scenario |  |  |  |  | TC
Super Admin Login
Add Employee | • Add personal information • Add contact information • Add work details • Add dependents • Add attachment • Add Notes • Add coverage • Update covered members • Terminate medical • Add additional insurance • Declined plans • Audit details • Load roaster • Rehire • Reinstate • Enroll Cobra |  |  |  |  | 50
Account Information | • Edit account • Add contacts • View broker • Browse attachment and save • Add notes |  |  |  |  | 150
Manage Coverage | • Enrollment notification • Enrollment roaster • Export • Update covered members • Notes • Attachment • Terminate Medical • Enroll Cobra |  |  |  |  | 250
Passive Renewal | • Renewal Center Access Setup > Renewal Center • Renewal Type Setup > Passive Renewal • Renewal Edit Enrollment • Send enrollment notification • Enrollment Roster |  |  |  |  | 200
Reporting | • Download reports • Create report • Edit report layout • Reset • Save report • Export • My report |  |  |  |  | 100
Carrier Response Update | • Update member id • Update success response • Search • Reset • Cancel |  |  |  |  | 150
Content Management | Page | · Add page |  |  |  | 10
|  | · Create page |  |  |  | 50
|  | · Edit | > Show properties |  |  | 80
|  | · Copy |  |  |  | 50
|  | · Preview |  |  |  | 60
|  | · Publish |  |  |  | 50
|  | · Unpublish |  |  |  | 60
|  | · Download |  |  |  | 50
| Review | · Edit | > Show properties > Save > Publish > Assign back > Preview > Cancel |  |  | 40
|  | · Preview |  |  |  | 20
|  | · Download |  |  |  | 30
| Documents | · Add document | > Select document > Document link |  |  | 50
|  | · Edit | > Save > Publish > Assign back > Preview > Cancel |  |  | 50
|  | · Copy |  |  |  | 40
|  | · Delete |  |  |  | 25
|  | · Unpublish |  |  |  | 20
| Banner | · Add banner | > Preview > Submit > Save |  |  | 30
|  | · Edit | > Publish > Preview |  |  | 30
|  | · Copy |  |  |  | 30
|  | · Preview |  |  |  | 30
|  | · Delete |  |  |  | 30
|  | · Unpublish |  |  |  | 30
| Images | · Upload image |  |  |  | 10
| Notifications | · Status | > On/Off |  |  | 10
|  | · Edit | > Save > Cancel |  |  | 10
| Section Titles | · Add section title | > Create section title > Cancel |  |  | 30
|  | · Edit | > Update section title > Cancel |  |  | 20
|  | · Delete |  |  |  | 20
Communication | Email log | · Download |  |  |  | 5
|  | · Preview |  |  |  | 5
|  | · Resend | > Send |  |  | 5
Reports | Reports | · Download |  |  |  | 15
|  | · Subscribe |  |  |  | 15
|  | · Unsubscribe |  |  |  | 15
Transactions | Transactions | · Account transactions | > Transaction details > Pending > Success > Failed |  |  | 10
|  | · Member transactions | > Transaction details > Pending > Success > Failed |  |  | 10
Others | Broker Management | · Add agency | > Save > Cancel |  |  | 15
|  | · Send notification | > Add attachment > Send > Close |  |  | 5
|  | · Terminate | > Yes > No |  |  | 10
|  | · Agency name | > Add contact | > Save > Cancel |  | 20
|  |  | > Send notification | > Add attachment > Send > Close |  | 5
|  |  | > Request access | > Ok |  | 5
|  |  | > Terminate | > Yes > No |  | 10
|  |  | > Contact | > Add account | > Save > Cancel > Back | 15
|  |  |  | > Terminate | > Yes > No | 15
| User Administration | User Profile | · Add user | > Reset > Cancel > Submit |  | 25
|  |  | · Edit | > Update > Cancel |  | 25
|  |  | · Delete | > Yes > No |  | 25
|  |  | · Request online access | > Ok |  | 5
|  |  | · Download |  |  | 5
|  | Account Contact User | · Add account contact | > Role > Reset > Cancel > Submit |  | 25
|  |  | · Edit |  |  | 25
|  |  | · Delete |  |  | 25
|  |  | · Request online access |  |  | 5
|  |  | · Download |  |  | 5
|  | Login History | · Download |  |  | 5
| Support User | · Login |  |  |  | 15
Settings | Global Settings | · Account Enrollment Controls | > Edit > Save > Cancel |  |  | 20
|  | · Account Preference Defaults | > Administrators | > Edit > Save > Cancel |  | 15
|  |  | > Employee access | > Edit > Save > Cancel |  | 15
|  |  | > Employee enrollment | > Edit > Save > Cancel |  | 15
|  |  | > Account | > Edit > Save > Cancel |  | 15
|  |  | > Dependents | > Edit > Save > Cancel |  | 5
|  | · Open Enrollment Date Restrictions | > Add restriction | > Save > Cancel |  | 5
|  | · Renewal Date Restrictions | > Add restriction | > Save > Cancel |  | 5
| Business Segment | · Business Segment | > Select business segment |  |  | 40
|  | · Administrators | > Edit > Save > Cancel
|  | · Employee Access | > Edit > Save > Cancel
|  | · Employee Enrollment | > Edit > Save > Cancel
|  | · Account | > Edit > Save > Cancel
|  | · Dependents | > Edit > Save > Cancel
| Account Specific | · Account list | > Administrators | > Edit > Save > Cancel |  | 100
|  |  | > Employee access | > Edit > Save > Cancel
|  |  | > Effective & Termination date setup | > Edit > Save > Cancel
|  |  | > Employee enrollment | > Edit > Save > Cancel
|  |  | > Account | > Browse > Edit > Save > Cancel
|  |  | > Dependents | > Edit > Save > Cancel
Alerts and Notifications | · Read |  |  |  |  | 15
· Search
My Profile | · View |  |  |  |  | 5
Reset Password | · Reset password |  |  |  |  | 5
| · Submit |  |  |  |  | 5
Submit | [5 empty] | 5
2505

## BIX-EDI
Test Scenario/Flow | TC | Status | Issue/Comment | Total | Completed | %
Group load Verification from back end and Front End compared with XML | 50 | Completed |  | 30 | 28 | 93.3333
Group and Membership load
IHA Group Transaction Trigger - Touch point Testing | 50 | Completed
New | 10 | Completed
Account Demographic Change | 20 | Completed
Account Contact Change | 10 | Completed
Account Address Change | 10 | Completed
Account BOR Change | 10 | Completed
GroupType Change To Content Only | 20 | Completed
GroupType Change To Transactional | 20 | Completed
Add Product | 10 | Completed
Terminate Product | 10 | Completed
Sub Account Addition | 10 | Completed
Sub Account Termination | 10 | Completed
Plan Change | 25 | Completed | Failed, sandeep is checking
Plan Correction | 50 | Completed | Failed, sandeep is checking
Multi Transaction | 80 | Completed
Renewal ( Initiate Passive renewal process ) | 30 | Completed
Group Termination a.Employer Portal Terminate Account Only b.Termination | 10 | Completed
Sc 1 : Transactional group with Membership - Termination date is Past from Todays date | 10 | Completed
Sc 2: Communication grp or Grp with out membership-Termination date is Past from Todays date | 10 | Completed
Sc 3: Transactional group with Membership-Termination date is Future from todays date | 10 | Completed
Sc 4: Communication grp or Grp with out membership-Termination date is Future from todays date | 10 | Completed
Employer Portal Terminate Account Only | 10 | Completed
Group and Membership mandatory Filed validation | 20 | Completed
BIX Route set up for IHA 834 File Delivery ( Full File and Change File ) | 25 | Completed
IHA 834 EDI Transaction set Segement and Element validation | 10 | Completed
IHA 834 EDI Scenario Testing | 15 | Completed
EDI Fields map to EE tables and columns | 10 | Completed
IC834 | 10 | Completed
575

## Common Testing
Types of Testing | Test case
User-Interface testing | 1.Text boxes - Make sure all the entered data is storing in the DB and the application is reflecting the saved data in UI 2.Select dropdowns - Make sure all the dropdown LOV are listing in UI 3.Calendars and buttons - Make sure calendar control is woring fine 4.Page navigation - Make sure all the pages are displaying as before 5.Display of images - Make sure all the UI images are displaying as expected. 6.Look and feel of the overall application
Data testing | 1.The schema - Backend validation to check all the table schema migrated after upgrade 2.Database tables - Backend validation to check all the DB tables migrated after the upgrade 3.Columns - Backend validation to check all the tables columns migrates after the upgrade 4.Keys and indexes - Backend validation to check all the keys and indexes are migrates after the upgrade 5.Stored procedures triggers - Backend validation to check all the stored procedures are migrated after the upgrade 6.Database server validations - Backend validation to check all the DB releated validations are migrated after the upgrade 7.Validating data duplication - Backend validation to check there is no duplication data created after the upgrade 8.Table rows/Data - Backend validation to check the data are migrated after the upgrade
Login and User Security
Performance Testing
Migration Testing | Verify if the queries executed in the new database yield same results as in the older one
Verify if the number of records in the old database and new database is the same. Here use appropriate automation tool
Verify that there are no redundancies and new database works exactly as the older one
Verify if the schema, relationships, table structures are unaltered or set back to match the old database image
Verify whether the changes made in application updates new database with correct values and type
Verify if after the new database connection is provided to all the components of the application. Application, server, interfaces, firewall, network connectivity etc.
Verify the query performance (time-taken to execute complex queries) of the new database is not more than earlier performance
Verify data handling for all the fields. Major challenges will be handling data for calendar dates, floating numbers, hexadecimal etc.

## Sheet1
S.No | Scenarios | Test Cases Count
1 | Group Dashboard | 36
2 | Tenant Dashboard | 66
3 | Add Employee | 36
4 | Activate Employee | 30
5 | Submit Employee | 24
6 | Activate and Enroll Employee | 48
7 | DeclineAll coverage | 36
8 | Terminate Medical | 36
6 | Terminate Medicare | 36
7 | Terminate Ancillary | 36
8 | Summary Verification | 27
9 | View benefits and SBC | 12
10 | CC Letter verification | 2
11 | Renroll Medical | 45
12 | Renroll Medicare | 15
13 | Reenroll Ancillary | 30
14 | Change Plan Medical | 45
15 | Change Plan Medicare | 15
16 | Change Plan Ancillary | 30
17 | Change coverage amount | 30
18 | Enroll and maintenance with Rate edit plan | 30
19 | QE on Medical | 45
20 | QE Medicare | 15
21 | QE Ancillary | 30
22 | Update covered Members - Medical | 108
23 | Update covered Members - Ancillary | 72
24 | Terminate Employee | 30
25 | Employe Rehire &Enroll | 30
26 | Reinstate employee | 60
27 | Retro enrollment with retro period | 72
28 | Retro termination with retro period | 117
| Total Count | 1244