## Plan
Activities | Assignee | Estimate | Dates
Framework Preparation | Swetha | 16 Days
JDK and Intellij setup and preparing required libs in pom.xml | Swetha,Deepika & Asif | Day 1 | 2023-02-16
Creating folder structure | Swetha | Day 2 | 2023-02-17
Downloading Drivers and Preparing Hooks file | Swetha | Day 3 | 2023-02-21
Preparing Wrappers for the Driver | Swetha | Day 4 & 5 | 2023-02-22
Test data mapping | Swetha | Day 6 & 7 | 2023-02-24
Logger | Swetha | Day 8 | 2023-02-27
Identifying the properties and placing them Config file | Swetha | Day 9 | 2023-02-28
Properties reader | Swetha | Day 10 | 2023-03-01
Basic application related Business functions | Swetha | Day 11 & 12 | 2023-03-02
Reporting | Swetha | Day 13 | 2023-03-03
Creating Basic test case and make it run | Swetha | Day 14 | 2023-03-06
Ensure the test case run from the testing file and from the maven plugin | Swetha | Day 15 | 2023-03-07
Cross-browser testing with the same test case | Swetha | Day 16 | 2023-03-08
Test Case preparation for Smoke Testing | Deepika & Asif | 2 Days
Login Page | Deepika & Asif | Day 2 | 2023-02-20
Home Page | Deepika & Asif | Day 2 | 2023-02-20
FBMC-Direct Bill Research Page | Deepika & Asif | Day 2 | 2023-02-20
Employee Administration Page | Deepika & Asif | Day 2 | 2023-02-20
Group Information Page | Deepika & Asif | Day 2 | 2023-02-20
Benefits Information Page | Deepika & Asif | Day 2 | 2023-02-20
Manage Coverage Page | Deepika & Asif | Day 3 | 2023-02-21
View Coverage Page | Deepika & Asif | Day 3 | 2023-02-21
Renewal Page | Deepika & Asif | Day 3 | 2023-02-21
Carrier Resonse Update Page | Deepika & Asif | Day 3 | 2023-02-21
Reports Page | Deepika & Asif | Day 3 | 2023-02-21
Comments Roster Page | Deepika & Asif | Day 3 | 2023-02-21
Logout Page | Deepika & Asif | Day 3 | 2023-02-21
Test Case preparation for Sanity Testing | Deepika & Asif | 9 Days
Login | Deepika & Asif | Day 4 | 2023-02-22
Tenant Dashboard | Deepika & Asif | Day 4 | 2023-02-22
Group Dashboard | Deepika & Asif | Day 4 | 2023-02-22
Add Employee | Deepika & Asif | Day 4 | 2023-02-22
Activate employee | Deepika & Asif | Day 5 | 2023-02-23
Submit employee | Deepika & Asif | Day 5 | 2023-02-23
Activate and Enroll Employee | Deepika & Asif | Day 5 | 2023-02-23
Decline all coverage | Deepika & Asif | Day 5 | 2023-02-23
Terminate Medical | Deepika & Asif | Day 6 | 2023-02-24
Terminate Medicare | Deepika & Asif | Day 6 | 2023-02-24
Terminate Ancillary | Deepika & Asif | Day 6 | 2023-02-24
Summary Verification | Deepika & Asif | Day 6 | 2023-02-24
View benefits and SBC | Deepika & Asif | Day 7 | 2023-02-27
CC Letter verification | Deepika & Asif | Day 7 | 2023-02-27
Renroll Medical | Deepika & Asif | Day 7 | 2023-02-27
Renroll Medicare | Deepika & Asif | Day 7 | 2023-02-27
Reenroll Ancillary | Deepika & Asif | Day 8 | 2023-02-28
Change Plan Medical | Deepika & Asif | Day 8 | 2023-02-28
Change Plan Medicare | Deepika & Asif | Day 8 | 2023-02-28
Change Plan Ancillary | Deepika & Asif | Day 8 | 2023-02-28
Change coverage amount | Deepika & Asif | Day 9 | 2023-03-01
Enroll and maintenance with Rate edit plan | Deepika & Asif | Day 9 | 2023-03-01
QE on Medical | Deepika & Asif | Day 9 | 2023-03-01
QE Medicare | Deepika & Asif | Day 9 | 2023-03-01
QE Ancillary | Deepika & Asif | Day 10 | 2023-03-02
Update covered Members - Medical | Deepika & Asif | Day 10 | 2023-03-02
Update covered Members - Ancillary | Deepika & Asif | Day 10 | 2023-03-02
Terminate Employee | Deepika & Asif | Day 10 | 2023-03-02
Employe Rehire &Enroll | Deepika & Asif | Day 11 | 2023-03-03
Reinstate employee | Deepika & Asif | Day 11 | 2023-03-03
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Deepika & Asif | Day 11 | 2023-03-03
Retro enrollment with retro period | Deepika & Asif | Day 12 | 2023-03-05
Retro termination with retro period | Deepika & Asif | Day 12 | 2023-03-05
Framework Demo | Swetha | 1Day | 2023-03-09
Scripting for Smoke Testing | Swetha,Deepika&Asif | 1Day | 2023-03-10
Scripting for Sanity Testing | Swetha,Deepika&Asif | 15 Days
Login | Swetha,Deepika&Asif | 2023-03-09 | 2023-03-13
Tenant Dashboard | Swetha,Deepika&Asif | 2023-03-09 | 2023-03-13
Group Dashboard | Swetha,Deepika&Asif | 2023-03-09 | 2023-03-13
Add Employee | Swetha,Deepika&Asif | 2023-03-10 | 2023-03-14
Activate employee | Swetha,Deepika&Asif | 2023-03-10 | 2023-03-14
Submit employee | Swetha,Deepika&Asif | 2023-03-10 | 2023-03-14
Activate and Enroll Employee | Swetha,Deepika&Asif | 2023-03-13 | 2023-03-15
Decline all coverage | Swetha,Deepika&Asif | 2023-03-13 | 2023-03-15
Terminate Medical | Swetha,Deepika&Asif | 2023-03-13 | 2023-03-15
Terminate Medicare | Swetha,Deepika&Asif | 2023-03-14 | 2023-03-16
Terminate Ancillary | Swetha,Deepika&Asif | 2023-03-14 | 2023-03-16
Summary Verification | Swetha,Deepika&Asif | 2023-03-14 | 2023-03-16
View benefits and SBC | Swetha,Deepika&Asif | 2023-03-15 | 2023-03-17
CC Letter verification | Swetha,Deepika&Asif | 2023-03-15 | 2023-03-17
Renroll Medical | Swetha,Deepika&Asif | 2023-03-15 | 2023-03-17
Renroll Medicare | Swetha,Deepika&Asif | 2023-03-16 | 2023-03-20
Reenroll Ancillary | Swetha,Deepika&Asif | 2023-03-16 | 2023-03-20
Change Plan Medical | Swetha,Deepika&Asif | 2023-03-16 | 2023-03-20
Change Plan Medicare | Swetha,Deepika&Asif | 2023-03-17 | 2023-03-21
Change Plan Ancillary | Swetha,Deepika&Asif | 2023-03-17 | 2023-03-21
Change coverage amount | Swetha,Deepika&Asif | 2023-03-17 | 2023-03-21
Enroll and maintenance with Rate edit plan | Swetha,Deepika&Asif | 2023-03-20 | 2023-03-22
QE on Medical | Swetha,Deepika&Asif | 2023-03-20 | 2023-03-22
QE Medicare | Swetha,Deepika&Asif | 2023-03-20 | 2023-03-22
QE Ancillary | Swetha,Deepika&Asif | 2023-03-21 | 2023-03-23
Update covered Members - Medical | Swetha,Deepika&Asif | 2023-03-21 | 2023-03-23
Update covered Members - Ancillary | Swetha,Deepika&Asif | 2023-03-21 | 2023-03-23
Terminate Employee | Swetha,Deepika&Asif | 2023-03-22 | 2023-03-24
Employe Rehire &Enroll | Swetha,Deepika&Asif | 2023-03-22 | 2023-03-24
Reinstate employee | Swetha,Deepika&Asif | 2023-03-22 | 2023-03-24
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Swetha,Deepika&Asif | 2023-03-23 | 2023-03-27
Retro enrollment with retro period | Swetha,Deepika&Asif | 2023-03-23 | 2023-03-27
Retro termination with retro period | Swetha,Deepika&Asif | 2023-03-23 | 2023-03-27