## Summary
Type | Framework and Test Case Preparation |  |  | Framework Demo | Automation Scripting |  | Final Demo
Activities | Framework | Smoke TC | Sanity TC | Demo | Smoke Test | Sanity Test | Sanity Demo
Date | Feb 16th To Mar 10th | Feb 22nd To Feb 23rd | Feb 24th To Mar 8th | 13th March | 14th March | Mar 15th To May 8th | May 10th
Progress | Done | Done | Done | Done | Done | In Progress

## Plan
Activities | Assignee | Estimate | Dates | Status
Framework Preparation | Swetha | 16 Days | 16-Feb To 10-Mar
JDK and IntelliJ setup and preparing required libs in pom.xml | Swetha,Deepika & Anandh |  | 2023-02-16 | Done
Creating folder structure | Swetha |  | 2023-02-17 | Done
Downloading Drivers and Preparing Hooks file | Swetha |  | 2023-02-21 | Done
Preparing Wrappers for the Driver | Swetha |  | 2023-02-22 | Done
Test data mapping | Swetha |  | 2023-02-24 | Done
Logger | Swetha |  | 2023-02-28 | Done
Identifying the properties and placing them Config file | Swetha |  | 2023-03-01 | Done
Properties reader | Swetha |  | 2023-03-02 | Done
Basic application related Business functions | Swetha |  | 2023-03-03 | Done
Reporting | Swetha |  | 2023-03-07 | Done
Creating Basic test case and make it run | Swetha |  | 2023-03-08 | Done
Ensure the test case run from the testing file and from the maven plugin | Swetha |  | 2023-03-09 | Done
Cross-browser testing with the same test case | Swetha |  | 2023-03-10 | Done
Framework Demo | Swetha | 1Day | 2023-03-13 | Done
Test Case preparation for Smoke Testing | Deepika & Anandh | 2 Days | 22-Feb To 23-Feb | Done
Login Page | Deepika & Anandh |  | 2023-02-22 | Done
Home Page | Deepika & Anandh |  | 2023-02-22 | Done
FBMC-Direct Bill Research Page | Deepika & Anandh |  | 2023-02-22 | Done
Employee Administration Page | Deepika & Anandh |  | 2023-02-22 | Done
Group Information Page | Deepika & Anandh |  | 2023-02-22 | Done
Benefits Information Page | Deepika & Anandh |  | 2023-02-22 | Done
Manage Coverage Page | Deepika & Anandh |  | 2023-02-22 | Done
View Coverage Page | Deepika & Anandh |  | 2023-02-23 | Done
Renewal Page | Deepika & Anandh |  | 2023-02-23 | Done
Carrier Resonse Update Page | Deepika & Anandh |  | 2023-02-23 | Done
Reports Page | Deepika & Anandh |  | 2023-02-23 | Done
Comments Roster Page | Deepika & Anandh |  | 2023-02-23 | Done
Logout Page | Deepika & Anandh |  | 2023-02-23 | Done
Test Case preparation for Sanity Testing | Deepika & Anandh | 9 Days | 24-Feb To 8-Mar | Done
Login | Deepika & Anandh |  | 2023-02-24 | Done
Tenant Dashboard | Deepika & Anandh |  | 2023-02-24 | Done
Group Dashboard | Deepika & Anandh |  | 2023-02-24 | Done
Add Employee | Deepika & Anandh |  | 2023-02-24 | Done
Activate employee | Deepika & Anandh |  | 2023-02-27 | Done
Submit employee | Deepika & Anandh |  | 2023-02-27 | Done
Activate and Enroll Employee | Deepika & Anandh |  | 2023-02-27 | Done
Decline all coverage | Deepika & Anandh |  | 2023-02-27 | Done
Terminate Medical | Deepika & Anandh |  | 2023-02-28 | Done
Terminate Medicare | Deepika & Anandh |  | 2023-02-28 | Done
Terminate Ancillary | Deepika & Anandh |  | 2023-02-28 | Done
Summary Verification | Deepika & Anandh |  | 2023-02-28 | Done
View benefits and SBC | Deepika & Anandh |  | 2023-03-01 | Done
CC Letter verification | Deepika & Anandh |  | 2023-03-01 | Done
Renroll Medical | Deepika & Anandh |  | 2023-03-01 | Done
Renroll Medicare | Deepika & Anandh |  | 2023-03-01 | Done
Reenroll Ancillary | Deepika & Anandh |  | 2023-03-02 | Done
Change Plan Medical | Deepika & Anandh |  | 2023-03-02 | Done
Change Plan Medicare | Deepika & Anandh |  | 2023-03-02 | Done
Change Plan Ancillary | Deepika & Anandh |  | 2023-03-02 | Done
Change coverage amount | Deepika & Anandh |  | 2023-03-03 | Done
Enroll and maintenance with Rate edit plan | Deepika & Anandh |  | 2023-03-03 | Done
QE on Medical | Deepika & Anandh |  | 2023-03-03 | Done
QE Medicare | Deepika & Anandh |  | 2023-03-03 | Done
QE Ancillary | Deepika & Anandh |  | 2023-03-06 | Done
Update covered Members - Medical | Deepika & Anandh |  | 2023-03-06 | Done
Update covered Members - Ancillary | Deepika & Anandh |  | 2023-03-06 | Done
Terminate Employee | Deepika & Anandh |  | 2023-03-07 | Done
Employe Rehire &Enroll | Deepika & Anandh |  | 2023-03-07 | Done
Reinstate employee | Deepika & Anandh |  | 2023-03-07 | Done
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Deepika & Anandh |  | 2023-03-08 | Done
Retro enrollment with retro period | Deepika & Anandh |  | 2023-03-08 | Done
Retro termination with retro period | Deepika & Anandh |  | 2023-03-08 | Done
Scripting for Smoke Testing (just checking navigations to all pages of application) | Swetha,Deepika&Anandh | 1Day | 2023-03-14 | Done
Scripting for Sanity Testing |  |  | 15-Mar To 08-May
Login | Swetha&Anandh |  |  | Done
Tenant Dashboard | Swetha&Anandh |  |  | Done
Group Dashboard | Swetha&Anandh |  |  | Done
Add Employee | Swetha&Anandh |  |  | Done
Activate employee | Swetha&Anandh |  |  | Done
Submit employee | Swetha&Anandh |  |  | Done
Activate and Enroll Employee | Swetha&Anandh |  |  | Done
Decline all coverage | Swetha&Anandh |  |  | Done
Terminate Medical | Swetha&Anandh |  |  | Done
Terminate Medicare | Swetha&Anandh |  |  | Done
Terminate Ancillary | Swetha&Anandh |  |  | Done
Summary Verification | Swetha&Anandh |  |  | Done
View benefits and SBC | Swetha&Anandh |  |  | Done
CC Letter verification | Swetha&Anandh |  |  | Done
Renroll Medical | Swetha&Anandh |  |  | Done
Renroll Medicare | Swetha&Anandh |  |  | Done
Reenroll Ancillary | Swetha&Anandh |  |  | Done
Change Plan Medical | Swetha&Anandh |  |  | Done
Change Plan Medicare | Swetha&Anandh |  |  | Done
Change Plan Ancillary | Swetha&Anandh |  |  | Done
Change coverage amount | Swetha,Anil&Anandh |  |  | Done
Enroll and maintenance with Rate edit plan | Swetha,Anil&Anandh |  |  | Done
QE on Medical | Swetha&Anandh |  |  | Done
QE Medicare | Swetha,Anil&Anandh |  |  | Done
QE Ancillary | Swetha,Anil&Anandh |  |  | Done
Update covered Members - Medical | Swetha,Anil&Anandh |  |  | Done
Update covered Members - Ancillary | Swetha,Anil&Anandh |  |  | Done
Terminate Employee | Swetha,Anil&Anandh |  |  | Done
Employe Rehire &Enroll | Swetha,Anil&Anandh |  |  | Done
Reinstate employee | Swetha,Anil&Anandh |  |  | Done
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Swetha,Anil&Anandh |  |  | Done
Retro enrollment with retro period | Swetha,Anil&Anandh |  |  | Done
Retro termination with retro period | Swetha,Anil&Anandh |  |  | Done