## Plan
Activities | Assignee | Estimate | Dates
Framework Preparation | Swetha | 16 Days | 16-Feb To 10-Mar
JDK and IntelliJ setup and preparing required libs in pom.xml | Swetha,Deepika & Anandh |  | 2023-02-16
Creating folder structure | Swetha |  | 2023-02-17
Downloading Drivers and Preparing Hooks file | Swetha |  | 2023-02-21
Preparing Wrappers for the Driver | Swetha |  | 2023-02-22
Test data mapping | Swetha |  | 2023-02-24
Logger | Swetha |  | 2023-02-28
Identifying the properties and placing them Config file | Swetha |  | 2023-03-01
Properties reader | Swetha |  | 2023-03-02
Basic application related Business functions | Swetha |  | 2023-03-03
Reporting | Swetha |  | 2023-03-07
Creating Basic test case and make it run | Swetha |  | 2023-03-08
Ensure the test case run from the testing file and from the maven plugin | Swetha |  | 2023-03-09
Cross-browser testing with the same test case | Swetha |  | 2023-03-10
Framework Demo | Swetha | 1Day | 2023-03-13
Test Case preparation for Smoke Testing | Deepika & Anandh | 2 Days | 22-Feb To 23-Feb
Login Page | Deepika & Anandh |  | 2023-02-22
Home Page | Deepika & Anandh |  | 2023-02-22
FBMC-Direct Bill Research Page | Deepika & Anandh |  | 2023-02-22
Employee Administration Page | Deepika & Anandh |  | 2023-02-22
Group Information Page | Deepika & Anandh |  | 2023-02-22
Benefits Information Page | Deepika & Anandh |  | 2023-02-22
Manage Coverage Page | Deepika & Anandh |  | 2023-02-22
View Coverage Page | Deepika & Anandh |  | 2023-02-23
Renewal Page | Deepika & Anandh |  | 2023-02-23
Carrier Resonse Update Page | Deepika & Anandh |  | 2023-02-23
Reports Page | Deepika & Anandh |  | 2023-02-23
Comments Roster Page | Deepika & Anandh |  | 2023-02-23
Logout Page | Deepika & Anandh |  | 2023-02-23
Test Case preparation for Sanity Testing | Deepika & Anandh | 9 Days | 24-Feb To 8-Mar
Login | Deepika & Anandh |  | 2023-02-24
Tenant Dashboard | Deepika & Anandh |  | 2023-02-24
Group Dashboard | Deepika & Anandh |  | 2023-02-24
Add Employee | Deepika & Anandh |  | 2023-02-24
Activate employee | Deepika & Anandh |  | 2023-02-27
Submit employee | Deepika & Anandh |  | 2023-02-27
Activate and Enroll Employee | Deepika & Anandh |  | 2023-02-27
Decline all coverage | Deepika & Anandh |  | 2023-02-27
Terminate Medical | Deepika & Anandh |  | 2023-02-28
Terminate Medicare | Deepika & Anandh |  | 2023-02-28
Terminate Ancillary | Deepika & Anandh |  | 2023-02-28
Summary Verification | Deepika & Anandh |  | 2023-02-28
View benefits and SBC | Deepika & Anandh |  | 2023-03-01
CC Letter verification | Deepika & Anandh |  | 2023-03-01
Renroll Medical | Deepika & Anandh |  | 2023-03-01
Renroll Medicare | Deepika & Anandh |  | 2023-03-01
Reenroll Ancillary | Deepika & Anandh |  | 2023-03-02
Change Plan Medical | Deepika & Anandh |  | 2023-03-02
Change Plan Medicare | Deepika & Anandh |  | 2023-03-02
Change Plan Ancillary | Deepika & Anandh |  | 2023-03-02
Change coverage amount | Deepika & Anandh |  | 2023-03-03
Enroll and maintenance with Rate edit plan | Deepika & Anandh |  | 2023-03-03
QE on Medical | Deepika & Anandh |  | 2023-03-03
QE Medicare | Deepika & Anandh |  | 2023-03-03
QE Ancillary | Deepika & Anandh |  | 2023-03-06
Update covered Members - Medical | Deepika & Anandh |  | 2023-03-06
Update covered Members - Ancillary | Deepika & Anandh |  | 2023-03-06
Terminate Employee | Deepika & Anandh |  | 2023-03-07
Employe Rehire &Enroll | Deepika & Anandh |  | 2023-03-07
Reinstate employee | Deepika & Anandh |  | 2023-03-07
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Deepika & Anandh |  | 2023-03-08
Retro enrollment with retro period | Deepika & Anandh |  | 2023-03-08
Retro termination with retro period | Deepika & Anandh |  | 2023-03-08
Scripting for Smoke Testing (just checking navigations to all pages of application) | Swetha,Deepika&Anandh | 1Day | 2023-03-14
Scripting for Sanity Testing | Swetha,Deepika&Anandh | 23 Days | 15-Mar To 14-Apr
Login | Swetha,Deepika&Anandh |  | 2023-03-15
Tenant Dashboard | Swetha,Deepika&Anandh |  | 2023-03-15
Group Dashboard | Swetha,Deepika&Anandh |  | 2023-03-15
Add Employee | Swetha,Deepika&Anandh |  | 2023-03-15
Activate employee | Swetha,Deepika&Anandh |  | 2023-03-16
Submit employee | Swetha,Deepika&Anandh |  | 2023-03-17
Activate and Enroll Employee | Swetha,Deepika&Anandh |  | 2023-03-17
Decline all coverage | Swetha,Deepika&Anandh |  | 2023-03-20
Terminate Medical | Swetha,Deepika&Anandh |  | 2023-03-21
Terminate Medicare | Swetha,Deepika&Anandh |  | 2023-03-21
Terminate Ancillary | Swetha,Deepika&Anandh |  | 2023-03-21
Summary Verification | Swetha,Deepika&Anandh |  | 2023-03-22
View benefits and SBC | Swetha,Deepika&Anandh |  | 2023-03-23
CC Letter verification | Swetha,Deepika&Anandh |  | 2023-03-24
Renroll Medical | Swetha,Deepika&Anandh |  | 2023-03-24
Renroll Medicare | Swetha,Deepika&Anandh |  | 2023-03-27
Reenroll Ancillary | Swetha,Deepika&Anandh |  | 2023-03-28
Change Plan Medical | Swetha,Deepika&Anandh |  | 2023-03-28
Change Plan Medicare | Swetha,Deepika&Anandh |  | 2023-03-29
Change Plan Ancillary | Swetha,Deepika&Anandh |  | 2023-03-30
Change coverage amount | Swetha,Deepika&Anandh |  | 2023-03-31
Enroll and maintenance with Rate edit plan | Swetha,Deepika&Anandh |  | 2023-04-03
QE on Medical | Swetha,Deepika&Anandh |  | 2023-04-04
QE Medicare | Swetha,Deepika&Anandh |  | 2023-04-05
QE Ancillary | Swetha,Deepika&Anandh |  | 2023-04-06
Update covered Members - Medical | Swetha,Deepika&Anandh |  | 2023-04-06
Update covered Members - Ancillary | Swetha,Deepika&Anandh |  | 2023-04-10
Terminate Employee | Swetha,Deepika&Anandh |  | 2023-04-11
Employe Rehire &Enroll | Swetha,Deepika&Anandh |  | 2023-04-12
Reinstate employee | Swetha,Deepika&Anandh |  | 2023-04-12
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Swetha,Deepika&Anandh |  | 2023-04-13
Retro enrollment with retro period | Swetha,Deepika&Anandh |  | 2023-04-13
Retro termination with retro period | Swetha,Deepika&Anandh |  | 2023-04-14

## Estimated FP
Scenario/Flow | Test Status | Functional Points | Estimated Days
TPA LOGIN
Login | Pass | 5 | 1.09 | Total Sanity Cases | 33
Tenant Dashboard | Pass | 7 |  | Total FP's | 1749
Group Dashboard | Pass | 10 |  | Estimated FP's per /person | 25
Add Employee | Pass | 60 |  | Total /person (3 resources) | 23.3
Activate employee | Pass | 60 | 1.62
Submit employee | Pass | 62
Activate and Enroll Employee | Pass | 70 | 1.86
Decline all coverage | Pass | 70
Terminate Medical | Pass | 65 | 1.73
Terminate Medicare | Pass | 65
Terminate Ancillary | Pass | 65 | 2.26
Summary Verification | Pass | 65
View benefits and SBC | Pass | 40
CC Letter verification | Pass | 30 | 1
Renroll Medical | Pass | 45
Renroll Medicare | Pass | 45 | 1.2
Reenroll Ancillary | Pass | 45
Change Plan Medical | Pass | 60 | 1.6
Change Plan Medicare | Pass | 60
Change Plan Ancillary | Pass | 60 | 1.6
Change coverage amount | Pass | 60
Enroll and maintenance with Rate edit plan | Pass | 65 | 1.6
QE on Medical | Pass | 60
QE Medicare | Pass | 60 | 1.6
QE Ancillary | Pass | 60
Update covered Members - Medical | Pass | 55 | 1.46
Update covered Members - Ancillary | Pass | 55
Terminate Employee | Pass | 45 | 1.2
Employe Rehire &Enroll | Pass | 45
Reinstate employee | Pass | 45 | 1.66
Cascade Scenario (Class, Sub group, Address change, DOB,Medicare flag, Dependent add or remove) | Pass | 80
Retro enrollment with retro period | Pass | 65 | 1.73
Retro termination with retro period | Pass | 65
| Total FP's | 1749 | Total 23 Days